## 1
a | Response Summary
Question
| What is a key business benefit of SAFe? | To adapt quickly to changing technologies and economic conditions
Question
| Which core competency of the Lean Enterprise focuses on building quality in? | Team and Technical Agility
Question
| What is Business Agility? | The ability to compete and thrive in the digital age by quickly responding to market changes and emerging opportunities with innovative business Solutions.
Question
| Which core competency of the Lean Enterprise addresses the integration across Agile Release Trains (ARTs)? | Enterprise Solution Delivery
Question
| A leader that admits his own mistakes exhibits which SAFe Core Value? | Transparency
Question
| The House of Lean is a classic metaphor describing the mindset essential for Lean thinking. Which one of the four pillars advocates a 'Go See' mindset? | Innovation
Question
| Which statement fits with the SAFe Core Value of Built-in Quality? | You cannot scale crappy code
Question
| Flow is one of the four pillars of the SAFe House of Lean. What are the three other pillars? (Choose three.) | Relentless improvement;Respect for people and culture;Innovation;
Question
| When basing decisions on economics, how are lead time, product cost, value, and development expense used? | To identify different parameters of the economic framework
Question
| Which is an aspect of systems thinking? | Optimizing a component does not optimize the system
Question
R | If small batches go through the system faster with lower variability, then which statement is true about batch size? | Low utilization increases variability | Large batches
Question
| What is an example of applying cadence-based synchronization in SAFe? | Teams align their Iterations to the same schedule to support communication, coordination, and system integration
Question
| According to SAFe Lean-Agile Principle #10, what should the Enterprise do when markets and Customers demand change? | Reorganize the network around the new value flow
Question
| Who facilitates team-level events? | The Scrum Master
Question
R | Who is the content authority for an Agile Release Train (ART)? | Solution Management | Product Owner
Question
R | Design Thinking identifies at least four new ways to measure success. What are two of those ways? (Choose two.) | Sustainability;Scalability; | Sustainbility
Question
| The benefit hypothesis justifies the Feature implementation cost, and what else? | It provides business perspective when making scope decisions
Question
R | During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To align the Business Owners' objectives to the release planning for the next PI | program risk and impediments
Question
R | What is the final activity on day one of Program Increment (PI) Planning? | Draft plan review | Management review and problem solving
Question
| In Program Increment (PI) Planning, the final plan review is done by who? | Teams and Business Owners
Question
| During Program Increment (PI) Planning, which statement is true about the activities of team breakouts? | At team breakout #2, teams work to create their final plans
Question
| What are three essential program events that keep the Agile Release Train (ART) on the tracks? (Choose three.) | System Demo;Inspect and Adapt (I&A) event;Program Increment (PI) Planning;
Question
| An Innovation and Planning (IP) Iteration allows time for which two activities? (Choose two.) | For continuing education;For innovation;
Question
R | What are two benefits of funding Value Streams rather than projects? (Choose two.) | To eliminate the delays in identifying key performance indicators to track progress;To eliminate the delays of project approvals and funding; | To eliminate the delays of project approvals and funding, Eliminate wastes
Question
| What are two aspects of leading by example? (Choose two.) | Authenticity;Life-long learning;
Question
R | According to John Kotter, what is the first step to successful change? | Developing the vision and strategy for change | Estabilish a sense of urgency
Question
| A compelling Vision for change achieves which two objectives? (Choose two.) | It motivates people to make the change;It clarifies the purpose and direction of the change;
Question
| Which two SAFe Program Consultant (SPC) resources are intended to aid in arriving at the SAFe tipping point? (Choose two.) | The Introducing SAFe workshop;The SAFe Executive Workshop Toolkit;
Question
| What is one key reason an organization starts a SAFe transformation? | A 'burning platform'; there is an obvious need to change a product or service
Question
R | A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Executives with high credibility;Trained Lean-Agile leaders;Product Management; | SPCs, Traind Lean-Agile Leaders, LACE
Question
R | What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To coordinate portfolio-level events;To foster SAFe communities of practice; | Communication Leadership and team training and coaching ART launches and coaching Agile tooling Consultant/Supplier coaching and training management
Question
| What are three benefits of organizing around Value Streams? (Choose three.) | Reduce hand-offs and faster delivery;Optimize the system as a whole;Built-in alignment between the business and development;
Question
| What are two types of Value Streams? (Choose two.) | Operational;Development;
Question
| What is the SAFe-recommended size of an effective Agile Release Train (ART)? | 50–125 people
Question
R | Why might an organization choose to create a platform Agile Release Train (ART)? | To accelerate value delivery | Set of services consumed by other ARTs OR use Shared services
Question
| Which statement is true about multiple Agile Release Train (ART) rollouts? | ART rollouts can be done sequentially or in parallel
Question
R | There are multiple Agile Release Trains (ART) identified from the Value Stream and ART Identification Workshop. The ideal ART to launch first is found at the intersection of which converging factors? | Leadership support, low-hanging fruit, unclear products, and high-quality deliverables | The ideal Agile Release Trains (ART) is found first at the intersection of the converging factors such as leadership support, clear products or solution, collaborating teams, and the significant program opportunity or challenge. Leadership support is important to facilitate the launching of the ART.
Question
| What is the benefit of timeboxing the preparation for the first Program Increment (PI) Planning event? | To minimize the expansion of work during preparation
Question
| The design of an Agile Release Train (ART) should remove what? | Silos that inhibit flow
Question
R | What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | Program roster;All managers names and titles;Facilities; | System Team, business owner, Agile team attandence, Shared services | ?
Question
R | What are the elements of the Agile Release Train (ART) quickstart approach? | SAFe Product Owner/Product Manager training, SAFe Scrum Master training, SAFe for Teams training | Trainning, PI planning and workshop
Question
R | When are the teams formed for the Agile Release Train (ART)? | During the Value Stream and ART Identification Workshop | prior to PI planning
Question
R | What are two benefits of 'big room training'? (Choose two.) | Alignment to business objectives;Accelerated learning; | cost efficentncy, accelrated trainng, collective learning | https://www.scaledagileframework.com/train-teams-and-launch-the-art/
Question
| Why is Program Increment (PI) Planning itself considered a short-term win? | It creates a clear commitment to goals
Question
| Why is the first Program Increment (PI) the most crucial to facilitate? | Existing team, program, and organizational impediments become highly visible
Question
| Why does a SAFe Program Consultant (SPC) provide ongoing program consulting and team coaching? | To build the organization's Lean-Agile capabilities
Question
R | Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To make sure program-level items are addressed | To give the Agile Release Train the tools it needs to improve its performance To maximize the items for improvement for the first PI
Question
| A new Agile Release Train (ART) is formed and Lee is the new coach. All members of the train are new to Agile. After three Iterations Lee is hearing that many of the teams are having problems running their team events. What can she do to assist the teams? | Attend the Iteration Retrospectives as this will give her the most opportunity to help the teams
Question
| What are three parts to the Inspect and Adapt (I&A) event? (Choose three.) | Program Increment (PI) System Demo;Problem-solving workshop;Quantitative measurement;
Question
| When calculating and assessing team Program Increment (PI) performance for the PI predictability measure, which statement is true about the actual total? | It includes uncommitted objectives
Question
| A problem-solving workshop focuses the Agile Release Train (ART) to take what action? | To identify the root causes of the problems
Question
| When is the right time to create the role of the Solution Train Engineer (STE)? | When a large Value Stream has enough Agile Release Trains (ARTs) to launch a Solution Train
Question
| What is an example of traditional mindset for Lean Portfolio Management? | Centralized annual planning
Question
R | When should a Lean portfolio be established? | When required by management because it is better to operate in a completely decentralized environment | When the lack of communication between strategy and execution is hurting value delivery
Question
| What are two benefits of communities of practice? (Choose two.) | They increase coordination/synergy across units;They provide access to expertise;
Question
| How can Essential SAFe be used to evaluate a Full SAFe implementation? | Verify that the Full SAFe implementation performs the elements of Essential SAFe correctly
Question
| Which SAFe core competency includes fostering an innovative culture? | Continuous Learning Culture
Question
R | Which statement is true about the accelerate step of the SAFe Implementation Roadmap? | It is the time to consolidate gains by launching more Agile Release Trains and value streams | To reinforce and accelerate the SAFe transformation, leaders must now expand their view of the implementation. They will need to maintain the energy and enthusiasm they are devoting to the short cycles of Iterations and Program Increments (PIs) while setting their sights on the larger goals of true business agility. Across all seven competencies of the Lean Enterprise, improvements must progress to an advanced state until the culture of the organization transforms.
Question
| What is the last step in Kotter's eight step model to implementing successful change? | Anchor new approaches in the culture
Question
R | Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Solution Management;Solution Train Engineer (STE);Release Train Engineer (RTE); | Scrum Masterm RTE, and STE

## 2
a | Response Summary
Question
| What is a key business benefit of SAFe? | To adapt quickly to changing technologies and economic conditions
Question
| Which core competency of the Lean Enterprise focuses on building quality in? | Team and Technical Agility
Question
| What is Business Agility? | The ability to compete and thrive in the digital age by quickly responding to market changes and emerging opportunities with innovative business Solutions.
Question
| Which core competency of the Lean Enterprise addresses the integration across Agile Release Trains (ARTs)? | Enterprise Solution Delivery
Question
| A leader that admits his own mistakes exhibits which SAFe Core Value? | Transparency
Question
| The House of Lean is a classic metaphor describing the mindset essential for Lean thinking. Which one of the four pillars advocates a 'Go See' mindset? | Innovation
Question
| Which statement fits with the SAFe Core Value of Built-in Quality? | You cannot scale crappy code
Question
| Flow is one of the four pillars of the SAFe House of Lean. What are the three other pillars? (Choose three.) | Relentless improvement;Innovation;Respect for people and culture;
Question
| When basing decisions on economics, how are lead time, product cost, value, and development expense used? | To identify different parameters of the economic framework
Question
| Which is an aspect of systems thinking? | Optimizing a component does not optimize the system
Question
| If small batches go through the system faster with lower variability, then which statement is true about batch size? | Large batches can cause projects to miss targets
Question
| What is an example of applying cadence-based synchronization in SAFe? | Teams align their Iterations to the same schedule to support communication, coordination, and system integration
Question
| According to SAFe Lean-Agile Principle #10, what should the Enterprise do when markets and Customers demand change? | Reorganize the network around the new value flow
Question
| Who facilitates team-level events? | The Scrum Master
Question
R | Who is the content authority for an Agile Release Train (ART)? | The Product Owner | Product Management
Question
| Design Thinking identifies at least four new ways to measure success. What are two of those ways? (Choose two.) | Sustainability;Desirability;
Question
R | The benefit hypothesis justifies the Feature implementation cost, and what else? | It provides a high-level estimate of complexity | It provides business perspective when making scope decisions
Question
R | During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To gain commitment from each team to incrementally deliver value | To highlight challenges that management must address in the review and problem solving meeting
Question
| What is the final activity on day one of Program Increment (PI) Planning? | Management review and problem-solving
Question
R | In Program Increment (PI) Planning, the final plan review is done by who? | Business Owners and Scrum Masters | Teams and Business Owners
Question
| During Program Increment (PI) Planning, which statement is true about the activities of team breakouts? | At team breakout #2, teams work to create their final plans
Question
| What are three essential program events that keep the Agile Release Train (ART) on the tracks? (Choose three.) | Inspect and Adapt (I&A) event;Program Increment (PI) Planning;System Demo;
Question
| An Innovation and Planning (IP) Iteration allows time for which two activities? (Choose two.) | For innovation;For continuing education;
Question
| What are two benefits of funding Value Streams rather than projects? (Choose two.) | To eliminate the delays of project approvals and funding;People can keep working on the right feature for the right reasons when work takes longer than planned;
Question
| What are two aspects of leading by example? (Choose two.) | Authenticity;Life-long learning;
Question
| According to John Kotter, what is the first step to successful change? | Establishing a sense of urgency
Question
R | A compelling Vision for change achieves which two objectives? (Choose two.) | It clarifies the purpose and direction of the change;It lays out an action plan for completing the change; | It motivates people to make the change;It clarifies the purpose and direction of the change; | It motivates people to make the change;It clarifies the purpose and direction of the change;
Question
| Which two SAFe Program Consultant (SPC) resources are intended to aid in arriving at the SAFe tipping point? (Choose two.) | The SAFe Executive Workshop Toolkit;The Introducing SAFe workshop;
Question
| What is one key reason an organization starts a SAFe transformation? | A 'burning platform'; there is an obvious need to change a product or service
Question
R | A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Change agents trained as SAFe Program Consultants (SPCs);Product Management;Trained Lean-Agile leaders; | Executives with high credibility; Trained Lean-Agile leaders;Changeagents trained as SAFe Program Consultants (SPCs
Question
R | What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To help establish relentless improvement;To coordinate portfolio-level events; | To help establish relentless improvement;To foster SAFe communities of practice
Question
R | What are three benefits of organizing around Value Streams? (Choose three.) | Efficient utilization of Shared Services;Optimize the system as a whole;Reduce hand-offs and faster delivery; | Reduce hand-offs and faster delivery; Optimize the system as a whole; Built-in alignment between the business and development;
Question
| What are two types of Value Streams? (Choose two.) | Operational;Development;
Question
| What is the SAFe-recommended size of an effective Agile Release Train (ART)? | 50–125 people
Question
R | Why might an organization choose to create a platform Agile Release Train (ART)? | To reduce dependencies | To support architectural robustness
Question
R | Which statement is true about multiple Agile Release Train (ART) rollouts? | ART rollouts should be incremental; one ART should start when another reaches a 'sustain and improve' status | ART rollouts can be done sequentially or in parallel
Question
| There are multiple Agile Release Trains (ART) identified from the Value Stream and ART Identification Workshop. The ideal ART to launch first is found at the intersection of which converging factors? | Leadership support, collaborating teams, clear products or Solution, and significant program challenge or opportunity
Question
| What is the benefit of timeboxing the preparation for the first Program Increment (PI) Planning event? | To minimize the expansion of work during preparation
Question
| The design of an Agile Release Train (ART) should remove what? | Silos that inhibit flow
Question
R | What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | The portfolio canvas;Supplies;Facilities; | Facilities;Program roster;Supplies;
Question
| What are the elements of the Agile Release Train (ART) quickstart approach? | SAFe for Teams training, Program Increment (PI) Planning, workshops
Question
| When are the teams formed for the Agile Release Train (ART)? | Before the ART is launched but can be changed or adjusted if needed during the launch
Question
| What are two benefits of 'big room training'? (Choose two.) | Accelerated learning;Overall cost efficiency;
Question
| Why is Program Increment (PI) Planning itself considered a short-term win? | It creates a clear commitment to goals
Question
| Why is the first Program Increment (PI) the most crucial to facilitate? | Existing team, program, and organizational impediments become highly visible
Question
| Why does a SAFe Program Consultant (SPC) provide ongoing program consulting and team coaching? | To build the organization's Lean-Agile capabilities
Question
R | Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To maximize the items for improvement for the first Program Increment (PI) | To give the Agile Release Train the tools it needs to improve its performance
Question
| A new Agile Release Train (ART) is formed and Lee is the new coach. All members of the train are new to Agile. After three Iterations Lee is hearing that many of the teams are having problems running their team events. What can she do to assist the teams? | Attend the Iteration Retrospectives as this will give her the most opportunity to help the teams
Question
| What are three parts to the Inspect and Adapt (I&A) event? (Choose three.) | Program Increment (PI) System Demo;Problem-solving workshop;Quantitative measurement;
Question
| When calculating and assessing team Program Increment (PI) performance for the PI predictability measure, which statement is true about the actual total? | It includes uncommitted objectives
Question
| A problem-solving workshop focuses the Agile Release Train (ART) to take what action? | To identify the root causes of the problems
Question
| When is the right time to create the role of the Solution Train Engineer (STE)? | When a large Value Stream has enough Agile Release Trains (ARTs) to launch a Solution Train
Question
| What is an example of traditional mindset for Lean Portfolio Management? | Centralized annual planning
Question
| When should a Lean portfolio be established? | When the lack of communication between strategy and execution is hurting value delivery
Question
| What are two benefits of communities of practice? (Choose two.) | They increase coordination/synergy across units;They provide access to expertise;
Question
R | How can Essential SAFe be used to evaluate a Full SAFe implementation? | Customize Essential SAFe with constructs out of the Full SAFe | Verify that the Full SAFe implementation performs the elements of Essential SAFe correctly
Question
| Which SAFe core competency includes fostering an innovative culture? | Continuous Learning Culture
Question
| Which statement is true about the accelerate step of the SAFe Implementation Roadmap? | Remaining portfolios can leverage the learnings and successes of the initial portfolio adopting SAFe
Question
R | What is the last step in Kotter's eight step model to implementing successful change? | Consolidate gains and produce more change | Anchor new approaches in the culture
Question
R | Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Release Train Engineer (RTE);Solution Architect;Solution Train Engineer (STE); | STE,RTE, Enterprise Architect

## 3
Response Summary
Question
What is a key business benefit of SAFe? | To adapt quickly to changing technologies and economic conditions
Question
Which core competency of the Lean Enterprise focuses on building quality in? | Team and Technical Agility
Question
What is Business Agility? | The ability to compete and thrive in the digital age by quickly responding to market changes and emerging opportunities with innovative business Solutions.
Question
Which core competency of the Lean Enterprise addresses the integration across Agile Release Trains (ARTs)? | Enterprise Solution Delivery
Question
A leader that admits his own mistakes exhibits which SAFe Core Value? | Transparency
Question
The House of Lean is a classic metaphor describing the mindset essential for Lean thinking. Which one of the four pillars advocates a 'Go See' mindset? | Innovation
Question
Which statement fits with the SAFe Core Value of Built-in Quality? | You cannot scale crappy code
Question
Flow is one of the four pillars of the SAFe House of Lean. What are the three other pillars? (Choose three.) | Innovation;Respect for people and culture;Relentless improvement;
Question
When basing decisions on economics, how are lead time, product cost, value, and development expense used? | To identify different parameters of the economic framework
Question
Which is an aspect of systems thinking? | Optimizing a component does not optimize the system
Question
If small batches go through the system faster with lower variability, then which statement is true about batch size? | Large batches can cause projects to miss targets
Question
What is an example of applying cadence-based synchronization in SAFe? | Teams align their Iterations to the same schedule to support communication, coordination, and system integration
Question
According to SAFe Lean-Agile Principle #10, what should the Enterprise do when markets and Customers demand change? | Apply development cadence and synchronization to operate effectively and manage uncertainty | Reorganize the network around the new value flow
Question
Who facilitates team-level events? | The Scrum Master
Question
Who is the content authority for an Agile Release Train (ART)? | Product Management
Question
Design Thinking identifies at least four new ways to measure success. What are two of those ways? (Choose two.) | Sustainability;Desirability;
Question
The benefit hypothesis justifies the Feature implementation cost, and what else? | It provides business perspective when making scope decisions
Question
During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To highlight challenges that management must address in the management review and problem solving meeting
Question
What is the final activity on day one of Program Increment (PI) Planning? | Management review and problem-solving
Question
In Program Increment (PI) Planning, the final plan review is done by who? | Teams and Business Owners
Question
During Program Increment (PI) Planning, which statement is true about the activities of team breakouts? | At team breakout #2, teams work to create their final plans
Question
What are three essential program events that keep the Agile Release Train (ART) on the tracks? (Choose three.) | Program Increment (PI) Planning;Inspect and Adapt (I&A) event;System Demo;
Question
An Innovation and Planning (IP) Iteration allows time for which two activities? (Choose two.) | For innovation;For continuing education;
Question
What are two benefits of funding Value Streams rather than projects? (Choose two.) | People can keep working on the right feature for the right reasons when work takes longer than planned;To eliminate the delays of project approvals and funding;
Question
What are two aspects of leading by example? (Choose two.) | Life-long learning;Authenticity;
Question
According to John Kotter, what is the first step to successful change? | Establishing a sense of urgency
Question
A compelling Vision for change achieves which two objectives? (Choose two.) | It motivates people to make the change;It defines detailed metrics for the change; | It establishes a budget for the change initiative
Question
Which two SAFe Program Consultant (SPC) resources are intended to aid in arriving at the SAFe tipping point? (Choose two.) | The Introducing SAFe workshop;The SAFe Executive Workshop Toolkit;
Question
What is one key reason an organization starts a SAFe transformation? | A 'burning platform'; there is an obvious need to change a product or service
Question
A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Trained Lean-Agile leaders;Change agents trained as SAFe Program Consultants (SPCs);Executives with high credibility;
Question
What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To foster SAFe communities of practice;To help establish relentless improvement;
Question
What are three benefits of organizing around Value Streams? (Choose three.) | Built-in alignment between the business and development;Optimize the system as a whole;Reduce hand-offs and faster delivery;
Question
What are two types of Value Streams? (Choose two.) | Operational;Development;
Question
What is the SAFe-recommended size of an effective Agile Release Train (ART)? | 50–125 people
Question
Why might an organization choose to create a platform Agile Release Train (ART)? | To support architectural robustness
Question
Which statement is true about multiple Agile Release Train (ART) rollouts? | ART rollouts can be done sequentially or in parallel
Question
There are multiple Agile Release Trains (ART) identified from the Value Stream and ART Identification Workshop. The ideal ART to launch first is found at the intersection of which converging factors? | Leadership support, collaborating teams, clear products or Solution, and significant program challenge or opportunity
Question
What is the benefit of timeboxing the preparation for the first Program Increment (PI) Planning event? | To minimize the expansion of work during preparation
Question
The design of an Agile Release Train (ART) should remove what? | Silos that inhibit flow
Question
What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | Supplies;Facilities;Program roster;
Question
What are the elements of the Agile Release Train (ART) quickstart approach? | SAFe for Teams training, Program Increment (PI) Planning, workshops
Question
When are the teams formed for the Agile Release Train (ART)? | Before the ART is launched but can be changed or adjusted if needed during the launch
Question
What are two benefits of 'big room training'? (Choose two.) | Accelerated learning;Overall cost efficiency;
Question
Why is Program Increment (PI) Planning itself considered a short-term win? | It creates a clear commitment to goals
Question
Why is the first Program Increment (PI) the most crucial to facilitate? | Existing team, program, and organizational impediments become highly visible
Question
Why does a SAFe Program Consultant (SPC) provide ongoing program consulting and team coaching? | To build the organization's Lean-Agile capabilities
Question
Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To give the Agile Release Train (ART) the tools it needs to improve its performance
Question
A new Agile Release Train (ART) is formed and Lee is the new coach. All members of the train are new to Agile. After three Iterations Lee is hearing that many of the teams are having problems running their team events. What can she do to assist the teams? | Attend the Iteration Retrospectives as this will give her the most opportunity to help the teams
Question
What are three parts to the Inspect and Adapt (I&A) event? (Choose three.) | Program Increment (PI) System Demo;Quantitative measurement;Problem-solving workshop;
Question
When calculating and assessing team Program Increment (PI) performance for the PI predictability measure, which statement is true about the actual total? | It includes uncommitted objectives
Question
A problem-solving workshop focuses the Agile Release Train (ART) to take what action? | To identify the root causes of the problems
Question
When is the right time to create the role of the Solution Train Engineer (STE)? | When a large Value Stream has enough Agile Release Trains (ARTs) to launch a Solution Train
Question
What is an example of traditional mindset for Lean Portfolio Management? | Centralized annual planning
Question
When should a Lean portfolio be established? | When the lack of communication between strategy and execution is hurting value delivery
Question
What are two benefits of communities of practice? (Choose two.) | They provide access to expertise;They increase coordination/synergy across units;
Question
How can Essential SAFe be used to evaluate a Full SAFe implementation? | Customize Essential SAFe with constructs out of the Full SAFe | Verify that the Full SAFe implementation performs the elements of Essential SAFe correctly
Question
Which SAFe core competency includes fostering an innovative culture? | Continuous Learning Culture
Question
Which statement is true about the accelerate step of the SAFe Implementation Roadmap? | Remaining portfolios can leverage the learnings and successes of the initial portfolio adopting SAFe
Question
What is the last step in Kotter's eight step model to implementing successful change? | Anchor new approaches in the culture
Question
Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Enterprise Architect;Release Train Engineer (RTE);Solution Train Engineer (STE); | STE,RTE, Enterprise Architect

## 4
Response Summary
Question
| What is a key business benefit of SAFe? | To adapt quickly to changing technologies and economic conditions
Question
| Which core competency of the Lean Enterprise focuses on building quality in? | Team and Technical Agility
Question
| What is Business Agility? | The ability to compete and thrive in the digital age by quickly responding to market changes and emerging opportunities with innovative business Solutions.
Question
| Which core competency of the Lean Enterprise addresses the integration across Agile Release Trains (ARTs)? | Enterprise Solution Delivery
Question
| A leader that admits his own mistakes exhibits which SAFe Core Value? | Transparency
Question
foundation of house of lean | The House of Lean is a classic metaphor describing the mindset essential for Lean thinking. Which one of the four pillars advocates a 'Go See' mindset? | Innovation
Question
| Which statement fits with the SAFe Core Value of Built-in Quality? | You cannot scale crappy code
Question
| Flow is one of the four pillars of the SAFe House of Lean. What are the three other pillars? (Choose three.) | Relentless improvement;Respect for people and culture;Innovation;
Question
| When basing decisions on economics, how are lead time, product cost, value, and development expense used? | To identify different parameters of the economic framework
Question
| Which is an aspect of systems thinking? | Optimizing a component does not optimize the system
Question
| If small batches go through the system faster with lower variability, then which statement is true about batch size? | Large batches can cause projects to miss targets
Question
| What is an example of applying cadence-based synchronization in SAFe? | Teams align their Iterations to the same schedule to support communication, coordination, and system integration
Question
| According to SAFe Lean-Agile Principle #10, what should the Enterprise do when markets and Customers demand change? | Reorganize the network around the new value flow
Question
| Who facilitates team-level events? | The Scrum Master
Question
| Who is the content authority for an Agile Release Train (ART)? | Product Management
Question
| Design Thinking identifies at least four new ways to measure success. What are two of those ways? (Choose two.) | Sustainability;Desirability;
Question
| The benefit hypothesis justifies the Feature implementation cost, and what else? | It provides business perspective when making scope decisions
Question
| During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To highlight challenges that management must address in the management review and problem solving meeting
Question
| What is the final activity on day one of Program Increment (PI) Planning? | Management review and problem-solving
Question
| In Program Increment (PI) Planning, the final plan review is done by who? | Teams and Business Owners
Question
| During Program Increment (PI) Planning, which statement is true about the activities of team breakouts? | At team breakout #2, teams work to create their final plans
Question
| What are three essential program events that keep the Agile Release Train (ART) on the tracks? (Choose three.) | Inspect and Adapt (I&A) event;System Demo;Program Increment (PI) Planning;
Question
| An Innovation and Planning (IP) Iteration allows time for which two activities? (Choose two.) | For continuing education;For innovation;
Question
| What are two benefits of funding Value Streams rather than projects? (Choose two.) | People can keep working on the right feature for the right reasons when work takes longer than planned;To eliminate the delays of project approvals and funding;
Question
| What are two aspects of leading by example? (Choose two.) | Authenticity;Life-long learning;
Question
| According to John Kotter, what is the first step to successful change? | Establishing a sense of urgency
Question
| A compelling Vision for change achieves which two objectives? (Choose two.) | It motivates people to make the change; It clarifies the purpose and direction of the change;
Question
| Which two SAFe Program Consultant (SPC) resources are intended to aid in arriving at the SAFe tipping point? (Choose two.) | The SAFe Executive Workshop Toolkit;The Introducing SAFe workshop;
Question
| What is one key reason an organization starts a SAFe transformation? | A 'burning platform'; there is an obvious need to change a product or service
Question
| A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Trained Lean-Agile leaders;Change agents trained as SAFe Program Consultants (SPCs);Executives with high credibility;
Question
| What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To foster SAFe communities of practice;To help establish relentless improvement;
Question
| What are three benefits of organizing around Value Streams? (Choose three.) | Optimize the system as a whole;Built-in alignment between the business and development;Reduce hand-offs and faster delivery;
Question
| What are two types of Value Streams? (Choose two.) | Development;Operational;
Question
| What is the SAFe-recommended size of an effective Agile Release Train (ART)? | 50–125 people
Question
| Why might an organization choose to create a platform Agile Release Train (ART)? | To support architectural robustness
Question
| Which statement is true about multiple Agile Release Train (ART) rollouts? | ART rollouts can be done sequentially or in parallel
Question
| There are multiple Agile Release Trains (ART) identified from the Value Stream and ART Identification Workshop. The ideal ART to launch first is found at the intersection of which converging factors? | Leadership support, collaborating teams, clear products or Solution, and significant program challenge or opportunity
Question
| What is the benefit of timeboxing the preparation for the first Program Increment (PI) Planning event? | To minimize the expansion of work during preparation
Question
| The design of an Agile Release Train (ART) should remove what? | Silos that inhibit flow
Question
| What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | Supplies;Facilities;Program roster;
Question
| What are the elements of the Agile Release Train (ART) quickstart approach? | SAFe for Teams training, Program Increment (PI) Planning, workshops
Question
| When are the teams formed for the Agile Release Train (ART)? | Before the ART is launched but can be changed or adjusted if needed during the launch
Question
| What are two benefits of 'big room training'? (Choose two.) | Accelerated learning;Overall cost efficiency;
Question
| Why is Program Increment (PI) Planning itself considered a short-term win? | It creates a clear commitment to goals
Question
| Why is the first Program Increment (PI) the most crucial to facilitate? | Existing team, program, and organizational impediments become highly visible
Question
| Why does a SAFe Program Consultant (SPC) provide ongoing program consulting and team coaching? | To build the organization's Lean-Agile capabilities
Question
| Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To give the Agile Release Train (ART) the tools it needs to improve its performance
Question
| A new Agile Release Train (ART) is formed and Lee is the new coach. All members of the train are new to Agile. After three Iterations Lee is hearing that many of the teams are having problems running their team events. What can she do to assist the teams? | Attend the Iteration Retrospectives as this will give her the most opportunity to help the teams
Question
| What are three parts to the Inspect and Adapt (I&A) event? (Choose three.) | Problem-solving workshop;Program Increment (PI) System Demo;Quantitative measurement;
Question
| When calculating and assessing team Program Increment (PI) performance for the PI predictability measure, which statement is true about the actual total? | It includes uncommitted objectives
Question
| A problem-solving workshop focuses the Agile Release Train (ART) to take what action? | To identify the root causes of the problems
Question
| When is the right time to create the role of the Solution Train Engineer (STE)? | When a large Value Stream has enough Agile Release Trains (ARTs) to launch a Solution Train
Question
| What is an example of traditional mindset for Lean Portfolio Management? | Centralized annual planning
Question
| When should a Lean portfolio be established? | When the lack of communication between strategy and execution is hurting value delivery
Question
| What are two benefits of communities of practice? (Choose two.) | They provide access to expertise;They increase coordination/synergy across units;
Question
| How can Essential SAFe be used to evaluate a Full SAFe implementation? | Verify that the Full SAFe implementation performs the elements of Essential SAFe correctly
Question
| Which SAFe core competency includes fostering an innovative culture? | Continuous Learning Culture
Question
| Which statement is true about the accelerate step of the SAFe Implementation Roadmap? | Remaining portfolios can leverage the learnings and successes of the initial portfolio adopting SAFe
Question
| What is the last step in Kotter's eight step model to implementing successful change? | Anchor new approaches in the culture
Question
| Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | All solution roles

## Result
| Response Summary 1 |  |  | Response Summary |  | Correct | Wrong 1 | Wrong 2
#N/A | If small batches go through the system faster with lower variability, then which statement is true about batch size? | Low utilization increases variability | Large batches | Who is the content authority for an Agile Release Train (ART)? | The Product Owner | Product Management | Solution Management, Product Owner
Who is the content authority for an Agile Release Train (ART)? | Who is the content authority for an Agile Release Train (ART)? | Solution Management | Product Owner | The benefit hypothesis justifies the Feature implementation cost, and what else? | It provides a high-level estimate of complexity | It provides business perspective when making scope decisions
#N/A | Design Thinking identifies at least four new ways to measure success. What are two of those ways? (Choose two.) | Sustainability;Scalability; | Sustainbility | During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To gain commitment from each team to incrementally deliver value | To highlight challenges that management must address in the review and problem solving meeting | To align the Business Owners' objectives to the release planning for the next PI | To gain commitment from each team to incrementally deliver value
During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | During Program Increment (PI) Planning, what is the primary objective of the draft plan review? | To align the Business Owners' objectives to the release planning for the next PI | program risk and impediments | In Program Increment (PI) Planning, the final plan review is done by who? | Business Owners and Scrum Masters | Teams and Business Owners | Business Owners and Scrum Masters
#N/A | What is the final activity on day one of Program Increment (PI) Planning? | Draft plan review | Management review and problem solving | A compelling Vision for change achieves which two objectives? (Choose two.) | It clarifies the purpose and direction of the change;It lays out an action plan for completing the change; | It motivates people to make the change;It clarifies the purpose and direction of the change;
#N/A | What are two benefits of funding Value Streams rather than projects? (Choose two.) | To eliminate the delays in identifying key performance indicators to track progress;To eliminate the delays of project approvals and funding; | To eliminate the delays of project approvals and funding, Eliminate wastes | A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Change agents trained as SAFe Program Consultants (SPCs);Product Management;Trained Lean-Agile leaders; | Executives with high credibility; Trained Lean-Agile leaders;Changeagents trained as SAFe Program Consultants (SPCs | Executives with high credibility; Trained Lean-Agile leaders; Product Management; | Change agents trained as SAFe Program Consultants (SPCs);Product Management;Trained Lean-Agile leaders;
#N/A | According to John Kotter, what is the first step to successful change? | Developing the vision and strategy for change | Estabilish a sense of urgency | What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To help establish relentless improvement;To coordinate portfolio-level events; | To help establish relentless improvement;To foster SAFe communities of practice | 1. To coordinate portfolio-level events; 2. To foster SAFe communities of practice; | 1. To help establish relentless improvement;22. To coordinate portfolio-level events;
A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | A sufficiently powerful guiding coalition consists of which three elements? (Choose three.) | Executives with high credibility;Trained Lean-Agile leaders;Product Management; | SPCs, Traind Lean-Agile Leaders, LACE | What are three benefits of organizing around Value Streams? (Choose three.) | Efficient utilization of Shared Services;Optimize the system as a whole;Reduce hand-offs and faster delivery; | Reduce hand-offs and faster delivery; Optimize the system as a whole; Built-in alignment between the business and development; | Efficient utilization of Shared Services;Optimize the system as a whole;Reduce hand-offs and faster delivery;
What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | What are two responsibilities of a Lean-Agile Center of Excellence (LACE)? (Choose two.) | To coordinate portfolio-level events;To foster SAFe communities of practice; | Communication Leadership and team training and coaching ART launches and coaching Agile tooling Consultant/Supplier coaching and training management | Why might an organization choose to create a platform Agile Release Train (ART)? | To reduce dependencies | To support architectural robustness | To accelerate value delivery | To reduce dependencies
Why might an organization choose to create a platform Agile Release Train (ART)? | Why might an organization choose to create a platform Agile Release Train (ART)? | To accelerate value delivery | Set of services consumed by other ARTs OR use Shared services | Which statement is true about multiple Agile Release Train (ART) rollouts? | ART rollouts should be incremental; one ART should start when another reaches a 'sustain and improve' status | ART rollouts can be done sequentially or in parallel | ART rollouts should be incremental; one ART should start when another reaches a 'sustain and improve' status
#N/A | There are multiple Agile Release Trains (ART) identified from the Value Stream and ART Identification Workshop. The ideal ART to launch first is found at the intersection of which converging factors? | Leadership support, low-hanging fruit, unclear products, and high-quality deliverables | The ideal Agile Release Trains (ART) is found first at the intersection of the converging factors such as leadership support, clear products or solution, collaborating teams, and the significant program opportunity or challenge. Leadership support is important to facilitate the launching of the ART. | What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | The portfolio canvas;Supplies;Facilities; | Facilities;Program roster;Supplies; | Program roster; All managers names and titles; Facilities; | The portfolio canvas; Supplies; Facilities;
What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | What are three things an Agile Release Train (ART) needs for its launch readiness? (Choose three.) | Program roster;All managers names and titles;Facilities; | System Team, business owner, Agile team attandence, Shared services | Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To maximize the items for improvement for the first Program Increment (PI) | To give the Agile Release Train the tools it needs to improve its performance | To make sure program-level items are addressed | To maximize the items for improvement for the first Program Increment (PI)
#N/A | What are the elements of the Agile Release Train (ART) quickstart approach? | SAFe Product Owner/Product Manager training, SAFe Scrum Master training, SAFe for Teams training | Trainning, PI planning and workshop | How can Essential SAFe be used to evaluate a Full SAFe implementation? | Customize Essential SAFe with constructs out of the Full SAFe | Verify that the Full SAFe implementation performs the elements of Essential SAFe correctly
#N/A | When are the teams formed for the Agile Release Train (ART)? | During the Value Stream and ART Identification Workshop | prior to PI planning | What is the last step in Kotter's eight step model to implementing successful change? | Consolidate gains and produce more change | Anchor new approaches in the culture
#N/A | What are two benefits of 'big room training'? (Choose two.) | Alignment to business objectives;Accelerated learning; | cost efficentncy, accelrated trainng, collective learning | Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Release Train Engineer (RTE);Solution Architect;Solution Train Engineer (STE); | STE,RTE, Enterprise Architect | Solution Management;Solution Train Engineer (STE);Release Train Engineer (RTE); | Release Train Engineer (RTE);Solution Architect;Solution Train Engineer (STE);
Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | Why is it important the SAFe Program Consultant (SPC) supports the Release Train Engineer (RTE) in the first problem-solving workshop? | To make sure program-level items are addressed | To give the Agile Release Train the tools it needs to improve its performance To maximize the items for improvement for the first PI
#N/A | When should a Lean portfolio be established? | When required by management because it is better to operate in a completely decentralized environment | When the lack of communication between strategy and execution is hurting value delivery
#N/A | Which statement is true about the accelerate step of the SAFe Implementation Roadmap? | It is the time to consolidate gains by launching more Agile Release Trains and value streams | To reinforce and accelerate the SAFe transformation, leaders must now expand their view of the implementation. They will need to maintain the energy and enthusiasm they are devoting to the short cycles of Iterations and Program Increments (PIs) while setting their sights on the larger goals of true business agility. Across all seven competencies of the Lean Enterprise, improvements must progress to an advanced state until the culture of the organization transforms.
Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Which three SAFe roles help coordinate between multiple Agile Release Trains (ARTs) within a Value Stream? (Choose three.) | Solution Management;Solution Train Engineer (STE);Release Train Engineer (RTE); | Scrum Masterm RTE, and STE